## Central_Tracker
SR.NO | Activity | Technology | Start Date | Status | Activity Description | Completion Date
1 | Selecting AUT | PROJECT MANAGEMENT | 2022-10-07 | COMPLETED | Going through different sources to find AUT | 2022-10-07
2 | Problem Statement | PROJECT MANAGEMENT | 2022-10-07 | COMPLETED | Finalizing Problem Statement | 2022-10-07
3 | Scrum Meetings | PROJECT MANAGEMENT | 2022-11-07 | COMPLETED | Daily Scrum Meetings | 2022-11-07
4 | Git Implemenetation | GIT | 30/09/2022 | COMPLETED | Creating repositories and setting it up on PSL Machines | 30/09/2022
5 | Manual Test Case Writing | MANUAL TESTING | 2022-12-07 | COMPLETED | Writing Manual Test cases for all the pages | 19/07/2022
6 | Scrum Meetings | PROJECT MANAGEMENT | 20/07/22 | COMPLETED | Daily Scrum Meetings | 20/07/22
7 | Meeting for Manual Test Case query | PROJECT MANAGEMENT | 22/07/2022 | COMPLETED | Reviewing the Manual Test Cases with Anuprita | 22/07/2022
8 | Maven Project for IRCTC | MAVEN | 26/07/2022 | COMPLETED | Setup Maven Dependencies for Automation Scripts | 26/07/2022
9 | Automating TestCases | SELENIUM | 27/07/2022 | COMPLETED | Automating Manual Test Cases using Selenium with Java | 2022-02-09
10 | Scrum Meetings | PROJECT MANAGEMENT | 2022-05-09 | COMPLETED | Daily Scrum Meetings | 2022-05-09
11 | Status Accounting Meeting | PROJECT MANAGEMENT | 23/09/2022 | COMPLETED | Status Accounting meeting with Anuprita | 23/09/2022
12 | Scrum Meetings | PROJECT MANAGEMENT | 25/09/2022 | COMPLETED | Daily Scrum Meetings | 25/09/2022
13 | REST API Implementation | POSTMAN | 30/09/2022 | COMPLETED | Postman used for creating environment and pre request scripts | 2022-02-10
14 | Creating Daily Activity Tracker | PROJECT MANAGEMENT | 2022-03-10 | COMPLETED | Creating Activity Tracker | 2022-03-10

## Project Management
SR.No | Activity | Activity Driven by | Start Date | Status | Blockers | Steps Taken to Resolved | Completion Date
Selecting AUT
1 | Selected AUT | ALL | 2022-10-07 | Completed | Finding Project as per needs | Exhaustive Searching | 2022-10-07
Problem Statement
1 | Problem Statement | ALL | 2022-10-07 | Completed | Unavailablity of Template | Created our own template | 2022-10-07
SYNC UP Meetings
1 | Meeting for manual testcases query | ALL | 22/07/2022 | Completed | Template for merging test cases | Implemented what the suggestions are provided by Anuprita | 22/07/2022
Scrum Meetings
1 | Application & Problem statement | ALL | 2022-11-07 | Completed |  |  | 2022-11-07
2 | Software Testing | ALL | 20/7/2022 | Completed |  |  | 20/7/2022
3 | Automation Selenium | ALL | 2022-05-09 | Completed |  |  | 2022-05-09
4 | After Updation | ALL | 25/9/2022 | Completed |  |  | 25/9/2022

## Git
Activity | Activity Driven by | Start Date | Status | Blockers | Steps Taken to Resolved | Completion Date
Git Implementation
1 | Created local repository | Manjiri Pathak | 30/09/2022 | Completed | Referred GIT Course | 30/09/2022

## Maven
Activity | Activity Driven by | Start Date | Status | Blockers | Steps Taken to Resolved | Completion Date
| Piyush Zope | 26/07/2022 | Completed | No Issues | Created Maven Project in Eclipse IDE. | 26/07/2022
Added Selenium Dependencies in pom.xml
Then, Build the project

## Manual Testing
Activity | Activity Driven by | Start Date | Status | Blockers | Steps Taken to Resolved | Completion Date
Manual Test Case Writing
1 | Piyush Zope Manjiri Pathak | 2022-12-07 | Completed | Scenario writing | Revisited Software Testing Selfy Shot | 13/07/2022
2 | Sanket Dhake Subhasmita Roy | 13/07/2022 | Completed | Test Cases | Revisited Software Testing Selfy Shot | 14/07/2022
3 | Amaan Syed Shubham Kumar | 15/07/2022 | Completed | ECP BVA | Revisited Software Testing Selfy Shot | 15/07/2022
4 | Pratham Verma Shamika Palyekar | 16/07/2022 | Completed | State Transfer Report | Revisited Software Testing Selfy Shot | 16/07/2022
5 | Ujjawal Rathore Shamika Palyekar | 16/07/2022 | Completed | Execution log | Revisited Software Testing Selfy Shot | 16/07/2022
6 | Manjiri Pathak Subhasmita Roy Shamika Palyekar | 17/07/2022 | Completed | Test Plan | Revisited Software Testing Selfy Shot | 19/07/2022

## Selenium Automation
Activity | Activity Driven by | Start Date | Status | Blockers | Steps Taken to Resolved | Completion Date
1 | Manjiri Phatak | 27/07/2022 | Completed | Automation scripts for Login Functionality | Referred Selenium With java Selfy Shot | 2022-06-08
2 | Sanket Dhake | 2022-08-08 | Completed | Automation Scripts for Search and PNR Status | Referred Selenium With java Selfy Shot | 20/8/2022
3 | Piyush Zope | 22/08/2022 | Completed | Automation Scripts for Ticket Booking and Cancellation | Referred Selenium With java Selfy Shot | 2022-02-09

## Postman
Activity | Activity Driven by | Start Date | Status | Blockers | Steps Taken to Resolved | Completion Date
| Piyush Zope Amaan Syed | 30/09/2022 | Completed | Environment Vatiables Set, Implemented Rest Methods , Import/Export, Test Validation , |  | 2022-02-10